## Status report+retail
base for the brand calendar
GLOBAL
WORKING TITLE (do not change) Campaign Name (Brand Calendar/virtual handover) | FINAL NAME campaign name (on platforms) | Products | Agency/ Contact | Project Owner+ channels Internal | Deliverables | [8 empty] | Delivery Date to markets/platforms | Comms Launch Date | Status | Next Steps | Next Steps | Brief | Creative Review | Market execution
[5 empty] | mov. | Print/OOH | Social | PR | DIG | Window guide-lines | Key visuals | Acti-vation guide-lines | Trans-lations
Brand or x-cat
Anthem | SPC/Anthem | Anthem | 180 LA | Ryan Morlan | x TV | x | x | x | x | x | x | x | x | Oct US, mid Nov rest world | Dec US, Jan/Feb rest world | Briefed |  | Creative development
Boost | Boost Technology incl Running Ultra Boost, Training, Womens Dance Boost, Outdoor | Ultra BOOST | Global Brand Design PDX | Minna Philipson / Josh Plante / Julia Baulig | x | x | x | x | x | x | x | x | x | Nov 25th | Feb 25th | Briefed |  | Creative development
Clima Chill | Clima Chill | clima chill technology incl running clima chill cosmic boost | tbc | Stephane Viarnaud | x tech/athletes | x | x | x | x | x | x | x | x | Feb 1st | April 1st | Briefed |  | Creative development
Infinite Series | Infinite Series | Training, Running, Football infinite products | Global Brand Design Herzo | Christy Kilmartin |  |  | x | x | x |  | x |  | x | Oct 1st Badge, Dec 1st Boost, Feb 1st Clima Chill | Dec 1st Badge, Feb 1st Boost, April 1st Clima Chill | Briefed |  | Creative development
Football
F50 | F50 (there will be haters) | f50, 11pro, Nitrocharg, Predator | Iris | Tom Ramsden |  | x | x | x | x | x | x |  | x | Nov 1st | Jan 23rd | Debriefed |  | await agency response prepare market workshop
Messi / Icon | Messi / Icon | Messi's signature boot Dec + March | Iris | Tom Ramsden |  | x | x | x | x | x | x |  | x | tbc | Nov 15 + Mar 16 | Debriefed |  | await agency response
Football Vault | Vault | Vault series | tbc | Tom Ramsden |  |  | x | [5 empty] | x | tbc | Dec ongoing | development |  | briefing
UCL | UCL | Ongoing engagement, ball and Final Berlin | tbc | Tom Ramsden |  |  | x | x | x |  |  |  | x | tbc | Ball Feb 1st + Final end May | development |  | briefing
A Clubs | A Clubs | jerseys | market agencies | Tom Ramsden | [7 empty] | x |  | GMM FW15 | FW15 | strategy development |  | guidelines to be shared with markets
LAM Copa America | Copa America | jerseys | LAM agency | Tom Ramsden | [7 empty] | x |  | tbc | tbc | strategy development |  | guidelines to be shared with markets
Originals
Superstar | Superstar | Superstar | tbc | Nadia Kokni | x TV tbc | x | x | x | x | x | x | x |  | Nov 1st | January 1st | finalizing concept |  | sign-off concept
Originals by Rita Ora | Originals by Rita Ora | Rita Ora | PL Studio / The Upside | Nadia Kokni | x teaser | x | x | x | x | x | x | x |  | tbc | SS15 (seasonal); peak in May | ongoing concept |  | plan SS15 production
Tubular | Tubular | Tubular | Lloyd | Nadia Kokni | x tbc | x | x | x | x | x | x | x |  | Jan 15th | March 15th | finalizing concept |  | sign-off concept
ZX Flux | #zxflux. Infinite. | ZX Flux | No update yet | Nadia Kokni | tbc animation | tbc | x | x | x | x | x |  |  | Dec 15th | Feb 15th | not started |  | write brief
Farm | Farm | Farm | No update yet | Nadia Kokni |  |  | x | x |  |  | x |  |  | tbc | tbc | No update yet |  | No update yet
SS15 Integrated Brand Toolkit | n/a | Retail Highlight Calendar/Comms Highlight Articles | PL Studio | Nadia Kokni | x | tbc | x | x | x | x | x | n/a |  | Sep 14th | SS15 (seasonal) | in planning for last week of July |  | sign off shot list
Fashion Calendar | weekly launches | refer to gtm activation calendar | No update yet | Leila Falaar |  |  | x | x | x |  |  |  |  | 4 weeks prior to launch | weekly | wip |  | deliver according to roll/out
Stan & Pharrell | No update yet | No update yet | No update yet | Melayne Weber | [9 empty] | October 1st | December 1st | No update yet | tbc | No update yet
Running
Springblade | Springblade | Springblade Drive | Global Brand Design PDX | Minna Philipson / Sean Peron / Julia Baulig |  | x | x | x | x | x | x |  | x | Sep 1st | Dec 1st | briefed |  | Creative development
Supernova BOOST | Supernova Glide BOOST | Supernova Glide BOOST | Global Brand Design PDX &TMS | Minna Philipson / Sean Peron / Julia Baulig |  | x | x | x | x | x | x |  | x | Sep 1st | Nov 1st | creative development |  | production
Running Product Stories | Running: Product Stories | Supernova, Springblade, Adizero, Aktiv, Climachill | Global Brand Design PDX | Minna Philipson / Sean Peron / Julia Baulig |  |  | x | x | x |  |  |  |  | Oct 1st | ongoing | briefed & concept development |  | 1st round concepts
Pure Boost | Pure Boost | Pure Boost | [11 empty] | Feb 1st | April 1st | Not a supported concept |  | not a supported concept
Markets
Basketball
NBA All-Star: Phase 1 | NBA all stars: Phase 1 | Various | Global Brand Design PDX | Lorrin Pascoe |  | x | x | x | x |  | x |  | x | Dec 1st | 2015-02-01 | Brief in Development | Finalize brief | Finalize brief
NBA All-Star: Phase 2 | NBA all stars: Phase 2 | Various | Global Brand Design PDX | Lorrin Pascoe |  | x | x | x | x | x | x | x | x | Jan 1st | 2015-02-01 | Brief in Development | Finalize brief | Finalize brief
Derrick Rose | Derrick Rose | Lakeshore | Global Brand Design PDX | Lorrin Pascoe |  |  | x | x | x |  | x |  | x | Dec 1st | 2015-02-01 | Brief in Development | Finalize brief | Finalize brief
NBA Playoffs/Finals | NBA Playoffs/Finals | NBA Jersey | Global Brand Design PDX | Lorrin Pascoe |  | x | x |  | x |  | x |  | x | March 1st | 2015-04-01 | Brief in Development | Finalize brief | Finalize brief
Training
Clima FW | Clima FW | clima ftw China | Global Brand Design Herzo | Stephane Viarnaud | x TV tbc | x | x | x | x | x | x | x | x | Jan 1st | April 1st | Waiting for brief |  | Briefing
Techfit | Techfit | Techfit | SAVVY | Stephane Viarnaud | [6 empty] | x |  |  | Oct 1st | Jan 1st | Briefing |  | Creative development
Climacool Aeroknit both genders | Climacool Aeroknit | Aeroknit | Global Brand Design Herzo | Stephane Viarnaud | [6 empty] | x |  |  | Feb 1st | Nov 1st | Finalizing briefing |  | Briefing
Womens/Stella
Stella Sport | adidas Stella Sport | No update yet | MadeThought/Alasdhair Willis | Lisann Costello / Karin Fichtl |  | x | x | x | x | x | x | x | x | Sep 30th | Dec 1st (launch Jan 15th), May window: Feb 28th | debriefed agency, waiting for concept |  | shoot
Womens Takeover (SH) | Womens Takeover | WT ftw | Made Thought | Lisann Costello / Karin Fichtl |  | x | x | x | x | x | x | x | x | March 1st | May 1st | concept creation |  | Creative development
Womens Training FW14 | Womens Training FW14 | FW14 Training | Made Thought | Lisann Costello / Reggie Casagrande | [6 empty] | x |  |  | Sep 30th | Dec 1st | concept creation |  | Creative development
Barricade | asmc Australian Open | barricade | Made Thought | Lisann Costello/ Anne Vasen | x |  | x | x | x | tbd | x |  |  | October | January | preproduction |  | shoot 1 Aug/Montreal
Barricade | asmc French Open | barricade | Made Thought | Lisann Costello/ Anne Vasen | x |  | x | x | x | tbd | x |  |  | December | May | preproduction |  | shoot 1 Aug/Montreal
adidas by Stella McCartney | adidas by Stella McCarntey | adidas by Stella McCarntey | Stella Creative Team | Lisann Costello/ Anne Vasen | x | x | x | x | x | x | x |  |  | October | January | preproduction |  | shoot 1 4 July/London
Outdoor
Terrex | Terrex | Agravic Pack | Stilbezirk | Johanna Vargas-Sotomonte | x | x | x | x | x | x | x | x | x | Q1: Oct 1st Q2: Dec 1st | Q1: Jan 1st Q2: Mar 1st | preproduction |  | production
All Outdoor | All Outdoor | EDO, Kids, HT | No update yet | No update yet | x (tech exp) |  |  | x |  |  | x |  | x | Q1: Oct 1st Q2: Dec 1st | Q1: Jan 1st Q2: Mar 1st | preproduction |  | production
NEO
Own Retail
Spring Brand Campaign | SS15 Spring Brand (& footwear) Campaign | Q1 Highlight products | happylucky | Anna Abenstein | x retail |  | x | x | x |  | x |  |  | October 31st | Jan 1st | briefed agency |  | creative review
SG Spring Campaign | SS15 Q1 Selena Gomez Campaign | Selena Gomez Q1 Range | happylucky | Kimberly Wallengren Katja Fiebig | x retail |  | x | x | x | x | x | x |  | December 31st | Feb 25th | briefed agency |  | creative review
Contemporary Sportswear | Contemporary Sportswear | No update yet | No update yet | No update yet | [9 empty] | No update yet | No update yet | No update yet |  | No update yet
Summer Brand Campaign | SS15 Summer Brand (& footwear) Campaign | Q2 Highlight products | happylucky | Anna Abenstein | x retail |  | x | x | x |  | x |  |  | January 31st | April 1st | briefed agency |  | creative review
OR Footwear | SS15 OR exclusive Footwear | Footwear from the OR exclusive range | No update yet | No update yet |  |  | x | x | x | x |  |  |  | No update yet | No update yet | No update yet |  | No update yet
Wholesale
Spring Brand Campaign | SS15 Spring Brand (& footwear) Campaign | Q1 Highlight products | happylucky | Anna Abenstein |  |  | x | x | x |  | x |  |  | October 31st | Jan 1st | briefed agency |  | creative review
SG Spring Campaign | SS15 Q1 Selena Gomez Campaign | Selena Gomez Q1 Range | happylucky | Kimberly Wallengren Katja Fiebig |  |  | x | x | x | x | x | x |  | December 31st | Feb 25th | briefed agency |  | creative review
Summer Brand Campaign | SS15 Summer Brand (& footwear) Campaign | Q2 Highlight products | happylucky | Anna Abenstein |  |  | x | x | x |  | x |  |  | January 31st | April 1st | briefed agency |  | creative review
SG Summer Campaign | SS15 Q2 Selena Gomez Campaign | Selena Gomez Q2 Range | happylucky | Kimberly Wallengren Katja Fiebig | [6 empty] | x |  |  | January 31st | April 1st | briefed agency |  | creative review
Action Sports
No update yet | No update yet | No update yet | No update yet | No update yet | [9 empty] | No update yet | No update yet | No update yet |  | No update yet
Tennis
Tennis campaign | barricade, adizero | No update yet | DieZwei | No update yet |  | x | x | x | x |  | x |  |  | No update yet | No update yet | No update yet | tbd | No update yet
Tennis social | social content | No update yet | No update yet | No update yet | x | x | x | x | x |  | x | x |  | No update yet | No update yet | No update yet | tbd | No update yet
Kids
Marvel Avengers | Marvel Avengers | SP youth and little kids | DieZWEI | Carolin Rucks |  |  | x | x | x | x | x | x | x | October 2014 | March 2015 | preproduction |  | production Miami
Star Wars | Star Wars | OR youth and little kids | DieZWEI | Carolin Rucks |  |  | x | x | x | x | x | x | x | October 2014 | 2015-01-01 | preproduction |  | production Miami
Wardrobe | Wardrobe | SP youth girls | DieZWEI | Carolin Rucks |  |  |  |  | x | x | x |  | x | October 2014 | Dec. 2015 | preproduction |  | production Miami
good vibrations | good vibrations | OR youth girls | DieZWEI | Carolin Rucks | [5 empty] | x | x |  |  | October 2014 | May 2015 | preproduction |  | production Miami
CMI | CMI | SP infants and little kids | DieZWEI | Carolin Rucks | [6 empty] | x |  |  | October 2014 | Dec.2014 | preproduction |  | production Miami
DtC
miadidas | No update yet | No update yet | No update yet | Matthias Wirkner |  |  | x |  | x |  | x |  |  | No update yet | No update yet | No update yet |  | No update yet
micoach 1 | No update yet | No update yet | No update yet | Philipp Schapitz | x |  | x | x | x |  | x |  |  | No update yet | No update yet | No update yet |  | No update yet
micoach 2 | No update yet | No update yet | No update yet | Philipp Schapitz | x |  | x | x | x |  | x |  |  | No update yet | No update yet | No update yet |  | No update yet
5 commerical campaigns eg outlet, sale, new arrival, MSS… | No update yet | No update yet | No update yet | Erin Camaioni |  |  |  |  | x |  | x |  |  | No update yet | No update yet | No update yet |  | No update yet
HBS
Rugby | All blacks jersey, rugby ftw, super rugby | all blacks jersey, rugby ftw,… | Iris | Shaun Anastasi | x social | x | x | x | x |  | x |  |  | All blacks jersey, rugby ftw and super rugby Mar 1st | Jersey/ftw: June 1st1 Super Rugby: 1 Mar | Awaiting direction from SpoMa |  | Align briefing
Rugby markets jerseys | French jersey, Italian jersey, | French jersey, Italian jersey, | TBWA France, tbc Italy | adidas France and adidas Italy | x social | x | x | x | x |  | x |  |  | No update yet | August | Global to receive briefs from markets |  | Global to approve brief
Rugby markets clubs | Stormers, Harlequins, Stade Francaise | clubs wear | More Mkt | adidas UK, SA and France | x social | x | x | x | x |  | x |  |  | No update yet | August | Delivered to markets |  | No update yet
Swim | Swim Beach | No update yet | Shaun Anastasi | Shaun Anastasi | [6 empty] | x |  |  | Dec 1st | Feb 1st | 1st half done |  | 2nd half to be shot in 3 months
Swim | Swim Performance | No update yet | Shaun Anastasi | Shaun Anastasi | x simple | [5 empty] | x |  |  | No update yet | No update yet | Preproduction |  | Production
Handball | Handball | No update yet | DieZwei | Shaun Anastasi | x simple | [5 empty] | x |  |  | Dec 1st | Feb 1st | Briefing |  | Preproduction
Cycling | Cycling | No update yet | UK | Shaun Anastasi | x simple | [5 empty] | x |  |  | Dec 1st | Feb 1st | Global writing brief |  | UK to develop
Cricket | Cricket | No update yet | Shaun Anastasi | Shaun Anastasi | x simple | [5 empty] | x |  |  | Dec 1st | Feb 1st | Products tbc |  | Briefing
Porsche Design Sport
No update yet | No update yet | No update yet | No update yet | Kathrin Buchert | [9 empty] | No update yet | No update yet | No update yet |  | No update yet
Y-3
No update yet | No update yet | No update yet | No update yet | Louise van Luschan | [9 empty] | No update yet | No update yet | No update yet |  | No update yet
Trend Marketing
No update yet | No update yet | No update yet | No update yet | Melayne Weber | [9 empty] | No update yet | No update yet | No update yet |  | No update yet

## info
category | first campaign idea | priority | channels
|  |  | TV (1 week) |  | ATL (1-4 weeks) |  | Retail window (4 weeks) |  | ISC (4 weeks) |  | Ecom (4 weeks) |  | Digital eg youtube (1 week) |  | Social (1-30days)
|  |  | launch | end | launch | end | launch | end | launch | end | launch | end | launch | end | launch | end
Brand/ x-cat | anthem | 1 | Jan 15 | Jan 22 | Jan 15 | Feb 10 | Jan 15 | Feb 10 | Jan 15 | Feb 10 | Jan 10 | Feb 08 | Jan 10 | Jan 18 | Jan 10 | Jan 11
| boost | 1 |  |  | Feb 20 | Mar 15 | Feb 20 | Mar 15 | Feb 20 | Mar 15 | Feb 15 | Mar 13 | Feb 15 | Feb 22 | Feb 15 | Feb 16
| climachill | 1 | Mar 03 | Mar 15 | Mar 15 | Mar28 | Mar 15 | Apr 10 | Mar 15 | Apr 10 | Mar 15 | Apr 10 | Mar 15 | Mar 22 | Mar 03 | Mar 13
Football | F50 | 1 |  |  | Jan 05 | Jan 30 | Jan 15 | Feb 10 | Jan 15 | Feb 10 | Jan 15 | Feb 10 | Jan 10 | Jan 18 | Jan 05 | Jan 12
| Messi | 2 |  |  | Nov 28 | Dec 20 | Nov 28 | Dec 25 | Nov 28 | Dec 25 | Nov 28 | Dec 25 | Nov 28 | Dec 05 | Nov 28 | Dec 05
Running | Springblade | 2 |  |  | Dec 10 | Dec 25 | Dec 10 | Jan 10 | Dec 10 | Jan 10 | Dec 10 | Jan 10 | Dec 15 | Dec 22 | Dec 15 | Dec 16
| Ultra boost | 2 | [6 empty] | Feb20 | Mar 15 | Feb20 | Mar 18
| Pure boost | 2 |  |  | Mar 20 | Apr 10 | Mar 20 | Apr 18 | Mar 20 | Apr 18 | Mar 10 | Apr 08 | Mar 15 | Mar22 | Mar 15 | Mar 20
Basketball | NBA play offs/March madness | 2 | [6 empty] | Feb 15 | Mar 12 |  |  | Feb 15 | Feb 22 | Feb 13 | Feb 14
Training (men, womens, kids) | aSMC | 2 |  |  | Feb 01 | Feb 28 | Feb 03 | Mar 05 | Feb 03 | Mar 05 | Feb 03 | Mar 05 | Feb 01 | Feb 10 | Feb 01 | Feb 02
| Stella sport | 2 |  |  | Jan 01 | Jan 25 | Jan 01 | Jan 31 | Jan 01 | Jan 29 | Jan 03 | Feb 02 | Jan 10 | Jan 17 | Jan 01 | Jan 02
| Womens takeover | 3 |  |  | May 09 | May 28 | May 09 | June 07 | May 09 | June 07 | May 01 | May 30 | May 01 | May 08 | May 01 | May 05
| Womens winter | 3 | [6 empty] | Dec 01 | Dec 31 | Nov 28 | Dec 20
| Womens (bra&pant) | 3 | [6 empty] | May 20 | June 15 | May 10 | June 08
| Womens boost | 3 | [6 empty] | Feb 12 | Mar 08
| Womens climachill | 3 | [6 empty] | Apr 22 | Mar 19
| Kids Superstars | 3 |  |  |  |  | Feb 28 | Mar 20 | Feb 28 | Mar 20
| Kids Starwars | 3 | [6 empty] | Jan 05 | Feb 05
| Kids Messi | 3 |  |  |  |  | Dec 01 | Dec 26 | Dec 01 | Dec 26
Outdoor | Terrex | 2 | Jan 01 | Jan 08 | Jan 06 | Jan 15 | Jan 06 | Feb 04 | Jan 06 | Feb 04 | Jan 06 | Feb 04 | Jan 06 | Jan 13 | Jan 06 | Jan 07
| All outdoor | 3 | [8 empty] | Dec 01 | Dec 25 |  |  | Dec 03 | Dec 10
Originals | ZX flux | 1 |  |  | Feb 18 | Feb 28 | Feb 16 | Mar 14 | Feb 16 | Mar 14 | Feb 16 | Mar 14 | Feb 14 | Feb 28 | Feb 14 | Feb 20
| Tubular | 1 |  |  | Apr 01 | Apr 28 | Apr 10 | May 10 | Apr 12 | May 09 | Apr 12 | May 10 | Apr 10 | Apr 20 | Apr 10 | Apr 11
| Superstar | 1 |  |  | Jan 10, Mar 20 | Feb 07, Apr 09 | Jan 10, Mar 20 | Feb 07, Apr 09 | Jan 10, Mar 20 | Feb 07, Apr 09 | Jan 10, Mar 20 | Feb 07, Apr 09 | Jan 08, Mar 18 | Jan 31, Apr 30 | Jan 08, Mar 18 | Jan 09, Mar 23
| Rita Ora | 1 |  |  | May 31 | Jun 15 | May 28 | Jun 25 | May 28 | Jun 25 | May 28 | Jun 25 | May 31 | Junr 06 | May 30 | June 03
| Stan Smith and friends | 3 |  |  |  |  | June 12 | July 10 | June 12 | July 10
| Originals blue | 3 |  |  |  |  | April 01 | April 30 | April 01 | April 30
| Originals Jeremy Scott | 3 |  |  |  |  | April 01 | April 30 | April 01 | April 30
| Originals Porsche | 3 |  |  |  |  | April 01 | April 30 | April 01 | April 30
| Originals Farm | 3 |  |  |  |  | April 01 | April 30 | April 01 | April 30
NEO/style | Selena Gomez | 1 |  |  | Feb 14 | Mar 03 | Feb 14 | Mar 14 | Feb 14 | Mar 14 | Feb 14 | Mar 14 | Feb 12 | Feb 28 | Feb 10 | Feb 18
| Summer brand campaign | 2 |  |  | Mar 02 | Mar 31 | Mar 05 | Apr 05 | Mar 05 | Apr 05 | Mar 05 | Apr 05 | Mar 03 | Mar 15 | Mar 02 | Mar 04
| Spring brand campaign | 2 |  |  | Jan 05 | Jan 30 | Jan 15 | Feb 15 | Jan 10 | Feb 10 | Jan 10 | Feb 10 | Jan 08 | Jan 31 | Jan 05 | Jan 07

## Prio 1 2 3 SS14 example
category | campaign name | priority | channels
|  |  | ATL | Key global events | Key local events | Retail | [5 empty] | .com |  |  |  | Digital/mobile experience | Email/CRM |  | Social
|  |  | activity dates | activity date | activity date | window |  |  | ISC |  |  | HP/CLP |  | PLP/PDP |  |  | activity dates |  | Facebook | [80 empty] | Twitter | [80 empty] | Instagram | [77 empty] | additional social channel
[6 empty] | activity dates |  |  | activity dates |  |  | activity dates |  | activity dates |  | activity dates |  |  | activity dates | [80 empty] | activity dates | [80 empty] | activity dates | [78 empty] | activity dates
Outdoor/Training | Climaheat/open all winter | 1 | 01.Nov-31.Jan |  |  | 1. Oct-1. Nov | 1. Nov- 1.Dec | 1.Dec- 1. Jan | 1. Oct-1. Nov | 1. Nov- 1.Dec | 1.Dec- 1. Jan | 1. Oct-1. Nov | 1. Nov- 31.Jan | 1. Oct-1. Nov | 1. Nov- 31.Jan |  | 1.Oct | 1. Nov | 20.9. | 25.9. | 1.10. | 7.10 | 10.10 | 15.10 | 18.10 | 21.10 | 26.10 | 1.11 | 2.11 | 3.11 | 4.11 | 6.11 | 8.11 | 9.11 | 11.11 | 12.11. | 14.11 | 15.11 | 17.11 | 18.11 | 20.11 | 21.11 | 22.11 | 23.11 | 25.11 | 26.11 | 27.11 | 29.11 | 30.11 | 1.12. | 2.12 | 4.12. | 5.12. | 6.12. | 7.12. | 9.12. | 10.12. | 11.12. | 13.12 | 14.12. | 15.12. | 16.12. | 18.12. | 19.12. | 20.12. | 21.12. | 22.12. | 23.12. | 25.12. | 26.12 | 27.12. | 28.12 | 30.12 | 31.12 | 2.1. | 3.1. | 4.1. | 6.1. | 7.1. | 8.1. | 9.1. | 11.1. | 12.1. | 13.1. | 14.1. | 15.1. | 16.1. | 18.1. | 20.1 | 21.1. | 22.1. | 23.1. | 24.1. | 25.1. | 27.1. | 28.1. | 29.1 | 30.1. | 31.1. | 20.9. | 25.9. | 1.10. | 7.10 | 10.10 | 15.10 | 18.10 | 21.10 | 26.10 | 1.11 | 2.11 | 3.11 | 4.11 | 6.11 | 8.11 | 9.11 | 11.11 | 12.11. | 14.11 | 15.11 | 17.11 | 18.11 | 20.11 | 21.11 | 22.11 | 23.11 | 25.11 | 26.11 | 27.11 | 29.11 | 30.11 | 1.12. | 2.12 | 4.12. | 5.12. | 6.12. | 7.12. | 9.12. | 10.12. | 11.12. | 13.12 | 14.12. | 15.12. | 16.12. | 18.12. | 19.12. | 20.12. | 21.12. | 22.12. | 23.12. | 25.12. | 26.12 | 27.12. | 28.12 | 30.12 | 31.12 | 2.1. | 3.1. | 4.1. | 6.1. | 7.1. | 8.1. | 9.1. | 11.1. | 12.1. | 13.1. | 14.1. | 15.1. | 16.1. | 18.1. | 20.1 | 21.1. | 22.1. | 23.1. | 24.1. | 25.1. | 27.1. | 28.1. | 29.1 | 30.1. | 31.1. | 20.9. | 25.9. | 1.10. | 7.10 | 10.10 | 15.10 | 18.10 | 21.10 | 26.10 | 1.11 | 2.11 | 3.11 | 4.11 | 6.11 | 8.11 | 9.11 | 11.11 | 12.11. | 14.11 | 15.11 | 17.11 | 18.11 | 20.11 | 21.11 | 22.11 | 23.11 | 25.11 | 26.11 | 27.11 | 29.11 | 30.11 | 1.12. | 2.12 | 4.12. | 5.12. | 6.12. | 7.12. | 9.12. | 10.12. | 11.12. | 13.12 | 14.12. | 15.12. | 16.12. | 18.12. | 19.12. | 20.12. | 21.12. | 22.12. | 23.12. | 25.12. | 26.12 | 27.12. | 28.12 | 30.12 | 31.12 | 2.1. | 3.1. | 4.1. | 6.1. | 7.1. | 8.1. | 9.1. | 11.1. | 12.1. | 13.1. | 14.1. | 15.1. | 16.1. | 18.1. | 20.1 | 21.1. | 25.1. | 27.1. | 28.1. | 29.1 | 30.1. | 31.1. |  |  | 22.1. | 23.1. | 24.1.
Running | Boost women | 2 | 26. Jul-26. Aug |  |  | 26. Jul-26. Aug |  |  | 26. Jul-26. Aug |  |  | 26. Jul-26. Aug |  | 26. Jul-26. Aug |  |  | 26. Jul |  | 23.7. | 27.7. | 01.8. | 02.8. | 03.8. | 05.8. | 07.8. | 09.8. | 11.8. | 14.8. | 16.8. | 18.8. | 20.8. | 23.8. | 24.8. | 25.8. | 28.8. | 30.8. | [63 empty] | 23.7. | 24.7. | 27.7. | 01.8. | 02.8. | 03.8. | 04.8. | 06.8. | 07.8. | 08.8. | 10.8. | 11.8. | 12.8. | 14.8. | 15.8. | 16.8. | 17.8. | 18.8. | 19.8. | 21.8. | 23.8. | 25.8. | 27.8. | 29.8. | [57 empty] | 26.7. | 3.8. | 10.8. | 26.8.
Womens | Bra&pant bar | 3 | / |  |  | / |  |  | 1. June-1. July |  |  | / |  | 1. Nov-1. Dec |  |  | / |  | 02.6. | 18.6. | 12.7. | [78 empty] | 22.7. | [11 empty] | 01.11. | [68 empty] | 08.6. | 23.7.